K R O G E R

Sourcing Automation

Build Task Plan — High-Level Milestones by Epic

Version 1.0  ·  Status: Draft for Kickoff  ·  September 2026

Source Inputs: M3 Sourcing Automation Requirements · Sourcing Automation Technical Design Document v1.0

Classification: Internal — Confidential

# How to Use This Document

This plan breaks the Sourcing Automation build into ~30 milestone-level tasks, organized by the M3 epics they satisfy. Two sections sit outside the epic structure because they're shared by every epic rather than owned by one: Section 0 (foundational data platform) must land before any detector can run, and Section 6 (backend, agent, safety) is the investigation-path surface every epic's opportunities are read and explained through. Each task lists its dependencies and any open decision or spec gap that needs resolving before or during the work — these are flagged, not glossed over, so they don't surface for the first time mid-sprint.

Resolve These Before Kickoff — They Gate Multiple Epics - Priority/tiering model (Open Question #1, tech spec §15): business hasn't picked a dollar threshold or scoring model yet. Recommend shipping with a simple static tier rule (e.g., three savings bands) so Epics 1–3 aren't blocked, and layering the full 5-component weighted scorer (§5) in once real dismissal data exists to calibrate it. - Agent architecture (Open Question #2): decide whether the Semantic Query Planner is a separate service or an in-process subgraph before building the LangGraph graph — this changes Section 6's build order and its own latency budget. - Two spec gaps need fresh design, not a straight port from the tech spec: the O3 volume-discount-loss sub-check (Epic 3) is currently just a comment with no query behind it, and O2's rebate/tier-proximity query references a registry join (r2) that isn't wired up in the sketch. - Recommended build order across epics: Foundational platform → Epic 1 (novel embedding work, reused nowhere else, so retire that risk first) → Epic 2 → Epic 3 → Epic 4 (lightweight, but land early since it's a dependency of the priority engine's feedback signal) → Epic 5 (gate on Document Digitization's M2 timeline; can run in parallel once the reference view exists) → Backend/Agent/Safety hardening → Observability & launch gates.

# Section 0 — Foundational Data Platform (Blocks All Epics)

The Bronze → Silver → Gold pipeline, the opportunity ontology, and the rule registry that every detector reads from. Nothing in Epics 1–5 can produce a real opportunity until this section is functional.

| # | Task | Description & Key Decisions | Depends On / Flags |
| --- | --- | --- | --- |
| 1 | Bronze ingestion | Stand up scheduled ingestion for the five Coupa Bronze tables (items, requisitions, purchase_orders, contracts, invoices) plus the Oracle AP base spend layer. Stamp process_date/_metadata per the existing GNFR pattern. | Oracle AP / EAA Bronze-Silver-Gold map doesn't exist yet (inherited open item from M1) — confirm timeline with Data Engineering before committing a date. |
| 2 | Silver line-grain parse | Explode nested Coupa JSON into typed line-grain tables: coupa_requisition_line, coupa_catalog_item, coupa_po_line, coupa_invoice_line. Route unparseable rows to DataQualityIssue rather than dropping them. | Depends on Task 1. |
| 3 | Gold opportunity ontology | Build SourcingOpportunity, ContractCoverage, SupplierProfile, ActionRequest, DataQualityIssue and the associated metric/fact views (gold_sourcing_opportunity, gold_contract_coverage_metric, supplier_concentration). | Depends on Task 2. |
| 4 | Rule registry (effective-dated config) | Build gold.opportunity_rule_registry as an append-only, effective-dated Delta table. Start with direct table edits under change-ticket discipline rather than a full self-serve admin API — the business hasn't finalized threshold values yet, so build the UI once the values are known. | Simplification recommendation — see kickoff callout above. |
| 5 | Data-quality gates | Implement the five run-time gates: source freshness, key completeness, embedding coverage, rule-registry integrity, and reconciliation-band check. A failed gate aborts the run and keeps the prior worklist rather than publishing a partial one. | Depends on Tasks 2–4. |
| 6 | Opportunity lifecycle + worklist cache | Build the opportunity_key dedup/merge logic (new → open → dismissed → actioned → auto_resolved), the priority-tier decision from the kickoff callout, and the Redis pre-warm job that refreshes category worklists post-publish. | Depends on Task 5. Priority model decision is a prerequisite, not a detail — resolve before this task starts. |

# Section 1 — Epic 1: Non-Catalog Spend with Catalog Equivalent Detection

The most technically novel epic — matching happens on meaning, not exact text, which is the one piece of this build that can't be a straightforward join.

| # | Task | Description & Key Decisions | Depends On / Flags |
| --- | --- | --- | --- |
| 7 | Embedding pipeline | Compute embeddings for every non-catalog requisition-line description and every catalog-item description; write to the Cosmos Vector DB index. | Depends on Section 0. Embedding refresh cadence and pipeline ownership are unresolved (Open Question #3) — confirm before scheduling. |
| 8 | Non-catalog match spine | Build gold.non_catalog_match_candidate: nearest-neighbor lookup with cosine similarity, match_confidence, and a match_band (high_confidence / candidate / below_floor). | Depends on Task 7. |
| 9 | Detector O1 | Build the O1 matcher: unit-price-delta × trailing-12-month quantity sizing, recurrence via description_cluster, minimum-savings floor from the rule registry, and unmatched-line routing to DataQualityIssue (unmatched_non_catalog). | Depends on Task 8. The 0.85 similarity floor is borrowed from an unrelated AI Gateway cache setting (Open Question #5) — plan a calibration pass against real query data before trusting it in production. |

# Section 2 — Epic 2: Contract Leakage and Reroute Recommendations

Lower technical risk than Epic 1 — this is mostly a join and a sizing formula — but it has a real business dependency that can stall it.

| # | Task | Description & Key Decisions | Depends On / Flags |
| --- | --- | --- | --- |
| 10 | Contract coverage resolution | Build the ContractCoverage join logic (supplier/category/date-range) that determines whether a line of spend is covered by an active or preferred contract. | Depends on Section 0. |
| 11 | Detector O2 — uncovered spend | Build the leakage sizing model: uncovered spend × estimated_discount_rate, per-category, read from the rule registry rather than hardcoded. | Depends on Task 10. Blocked on real business input — see Task 12. |
| 12 | Rebate/volume-tier proximity check | Build the companion check flagging spend approaching a rebate or volume-tier threshold. The sketch's registry join (r2) isn't wired to gold.active_rule — needs a clean implementation, not a direct port. | Depends on Task 10. |
| 13 | Per-category discount rates (business input) | Get actual negotiated discount rates per category from the business — the spec currently uses Carlos's facilities-example rate as a stand-in. Without this, O2's dollar figures are directionally right but not defensible in a business case. | Blocks Task 11 going to production; can build against placeholder rates in the meantime. |

# Section 3 — Epic 3: Supplier Consolidation Opportunities

Straightforward aggregation work, with one sub-feature that the tech spec hasn't actually designed yet.

| # | Task | Description & Key Decisions | Depends On / Flags |
| --- | --- | --- | --- |
| 14 | Supplier concentration view | Build the concentration aggregation (supplier_count, location_count, total_spend per item/category) that Detector O3 and the consolidation lane both read from. | Depends on Section 0. |
| 15 | Detector O3 — core consolidation | Flag items/categories over the configured supplier-count or fragmented-location floor; size using the consolidation-savings percentage from the rule registry. | Depends on Task 14. |
| 16 | Cross-location fragmentation | Confirm the location_count logic correctly identifies items bought separately across locations/divisions for the enterprise-pricing story, distinct from simple multi-supplier fragmentation. | Depends on Task 14. |
| 17 | Volume-discount-loss sub-check | Design and build this from scratch: flag frequent small non-preferred-vendor orders that are losing a volume discount already available through the preferred vendor's tier pricing. This needs its own savings formula (foregone tier discount), not the flat consolidation-savings percentage. | Spec gap — the tech spec has only a comment here, no query. Treat as net-new design work, not a port. |

# Section 4 — Epic 4: Recommendation Feedback and Outlier Learning

Lightweight to build, but land it early — the priority engine's feedback-adjusted-trust signal and every other epic's resurfacing logic depend on dismissals existing.

| # | Task | Description & Key Decisions | Depends On / Flags |
| --- | --- | --- | --- |
| 18 | Dismiss endpoint + reason taxonomy | Build the direct-write dismiss endpoint (no approval gate) with the five reason codes (ONE_OFF_EMERGENCY, ALREADY_ACTIONED, DATA_ERROR, NOT_A_REAL_MATCH, BUSINESS_JUSTIFICATION_OTHER) and the suppression-window field. | Depends on Section 0, Task 6. |
| 19 | Suppression window logic | Implement the dismissed → open lifecycle transition: a lapsed suppression window (180 days proposed) reopens the opportunity_key as a new evaluation rather than permanently suppressing it. | Suppression window length is an open business decision (Open Question #6) — confirm before hardcoding 180 days. |
| 20 | Dismissal feedback signal | Feed dismissal history into whichever prioritization model Task 6 lands on — either the full feedback_adjusted_trust scoring component, or a simpler 'frequently dismissed' flag if the priority engine starts simple. | Depends on Tasks 6 and 18. |
| 21 | Audit trail surface | Surface ActionRequest dismissal history per opportunity_key and category directly in the evidence panel, not as a separate report. | Depends on Task 18. |

# Section 5 — Epic 5: Total Landed Cost Comparison

The one epic with an external blocker. Build what's possible now; don't let it hold up the rest of the plan.

| # | Task | Description & Key Decisions | Depends On / Flags |
| --- | --- | --- | --- |
| 22 | Landed-cost reference view | Build gold.preferred_supplier_landed_cost (preferred unit price + average shipping per unit) as the comparison baseline for O4. | Depends on Section 0. |
| 23 | Detector O4 | Build the landed-cost variance detector, evaluating only invoice lines where landed_cost_ineligible = false (i.e., M2 OCR has populated shipping/freight). | Depends on Task 22 and M2 Document Digitization's line-item shipping/freight extraction (Open Question #8/#9). |
| 24 | Coverage reporting for O4 | Report O4's coverage percentage alongside its results rather than presenting a partial result set as complete — same pattern as Invoice Leakage's OCR-dependent detector. | Depends on Task 23. |
| 25 | M2 dependency checkpoint | Get a firm timeline from Document Digitization on when line-item shipping/freight extraction reaches usable coverage, and decide whether O4 ships in degraded mode now or waits for a coverage floor. | This is a cross-team scheduling task, not an engineering task — start it immediately regardless of where the rest of the build is. |

# Section 6 — Backend, Agent & Safety (Serves All Epics)

The investigation-path surface every epic's opportunities are explained and dismissed through. Can start in parallel with Sections 1–5 once Section 0's opportunity record contract is stable.

| # | Task | Description & Key Decisions | Depends On / Flags |
| --- | --- | --- | --- |
| 26 | Agent architecture decision | Decide whether the Semantic Query Planner is a standalone Kubernetes service (A2A call) or an in-process LangGraph subgraph before building the graph — this is currently an open question, not a settled design, and changes the shape of Task 28. | Do this before Task 28 starts, not alongside it. |
| 27 | FastAPI BFF endpoints | Build the REST surface: worklist, opportunity detail, evidence, dismiss (direct write), stage (HitL-gated), and the RBAC-gated admin/rules endpoints once Task 4's registry approach is settled. | Depends on Section 0. |
| 28 | LangGraph agent + tool boundary | Build the agent graph per the architecture decided in Task 26, with its read-only tool set (opportunity.find/get/evidence, find_supplier, query_spend_table, priority.explain) plus the two write tools (dismiss — direct; action.stage — HitL-gated) over Databricks MCP. | Depends on Tasks 26–27. |
| 29 | Content Safety integration | Wire Prompt Shields on requester/supplier-authored free text and OCR-extracted spans, and groundedness checking on every agent response against this run's tool results. | Depends on Task 28. This is the control that stops an invented savings figure from reaching a Coupa pre-fill — don't defer it to a later hardening pass. |
| 30 | HitL approval gate | Implement the threshold-based interrupt for staged cross-system actions (action.stage), distinct from the dismissal path which has no gate. | Depends on Task 28. |

# FageSection 7 — Observability, Evaluation & Launch Readiness

Build the core signals first; the full metric catalog in the tech spec can be filled in after launch once real traffic exists to tune alert thresholds against.

| # | Task | Description & Key Decisions | Depends On / Flags |
| --- | --- | --- | --- |
| 31 | Core metrics + alerting | Stand up matching-run health, dismissal_rate by opportunity_type/rule_version, groundedness score, and safety block rate first — these are the metrics that tell you whether the product is trustworthy, not just running. | Depends on Sections 0 and 6. |
| 32 | CI eval gates | Set up exact-match regression testing for detector output against a golden opportunity set, and for priority classification given an unchanged rule version, so drift is caught at merge time. | Depends on Sections 1–4 having stable detector output. |
| 33 | End-to-end staging walkthrough | Run the full path — nightly matching run through worklist load, investigation chat, and a dismissal — against staging data before any production cutover. | Depends on all prior sections. |
| 34 | Open-question closeout | Work through the remaining items from tech spec §15 that don't block a specific task above (Semantic Query Planner model choice, RFP-scope decision) so none are still open at GA. | Ongoing — track alongside the rest of the plan rather than as a final gate. |