## Readme
GNFR Trackers — Readme
Purpose
This workbook supports the GNFR initiative by tracking (1) the use cases to be delivered, and (2) the canonical data required to build each use case, including which source system(s) each canonical data element is sourced from. The Mapping tab is the primary working tab — it links use cases to canonical data elements using dropdowns sourced from the master Use Case Tracker and Canonical Data Tracker tabs, so requirements can be traced end-to-end from use case to source system.
Tab Guide
Tab | Purpose
Readme | This tab. Explains the workbook, tab purposes, dropdown mechanism, definitions, and version history.
Mapping | Start here. Links Use Case ID to Canonical Data ID (many-to-many) via dropdowns sourced from the Use Case Tracker and Canonical Data Tracker tabs, so you can see which canonical data each use case depends on, and which use cases depend on a given canonical data element.
Use Case Tracker | Master list of GNFR use cases to be delivered, with description, status, and notes. Selected via the Use Case ID dropdown on the Mapping tab.
Canonical Data Tracker | Master list of canonical data elements needed across use cases, with the source system(s) each is sourced from and traceability details (owner, extraction method, refresh frequency, status). One canonical data element may span multiple rows — one row per contributing source system — sharing the same Canonical Data ID. Selected via the Canonical Data ID dropdown on the Mapping tab.
Lists | Configurable dropdown source lists (Status, Data Domain, Source System, Extraction Method, Refresh Frequency, Canonical Data Element). Add new values within the listed range and they will automatically appear as dropdown options on the other tabs.
How the Configurable Dropdowns Work
All dropdown fields (Status, Data Domain, Source System, Extraction Method, Refresh Frequency, Canonical Data Element, and the Use Case ID / Canonical Data ID pickers on the Mapping tab) pull their options from named ranges defined on the Lists tab. To add a new option — e.g. a new source system or canonical data element — simply type it into the next blank cell in the relevant column on the Lists tab. Because each named range covers extra blank rows beyond the starter values, new entries are automatically picked up by the dropdowns on every other tab without editing any formulas or data validation settings.
Legend / Definitions
Term | Definition
GNFR | Goods Not For Resale — indirect spend categories (e.g. Marketing, Facilities, IT, Professional Services) that are not part of a company's resold product line.
Use Case | A specific business capability or outcome to be delivered as part of the GNFR initiative.
Canonical Data | A standardized, single source-of-truth data element that one or more use cases depend on, assembled from one or more source systems.
Source System | The originating system of record from which a canonical data element's underlying data is extracted (e.g. SAP, Ariba, Coupa).
Traceability | The ability to trace a canonical data element back to the source system(s) it came from, and forward to the use case(s) that depend on it.
Version History
Version | Date | Author | Changes
v1.0 | 2026-07-30 |  | Initial version
v1.1 | 2026-07-30 |  | Reordered tabs (Mapping is now the first working tab after Readme); added a configurable Canonical Data Element dropdown; removed Business Owner/Priority/Target Phase/Business Value columns from Use Case Tracker per user edits.

## Mapping
Mapping ID | Use Case ID | Use Case Name | Canonical Data ID | Canonical Data Element | Notes
M-001 | UC-001 | Spend Visibility | CD-001 | Purchase Order (PO) Data | ⚑ Flag for Siyang to review — Coupa PO data feeds the Spend Visibility semantic layer (spend totals by vendor/category).
M-002 | UC-001 | Spend Visibility | CD-002 | EAA Data (Marketing / Store Allocation) | ⚑ Flag for Siyang to review — EAA data feeds the Spend Visibility semantic layer alongside Coupa PO data.
M-003 | UC-002 | Document Digitization | CD-004 | Invoice Attachments | ⚑ Flag for Siyang to review — Invoice attachments are the direct input to the OCR digitization pipeline.
M-004 | UC-002 | Document Digitization | CD-003 | Invoice Data (AP) | ⚑ Flag for Siyang to review — Invoice (AP) line-item data is the modeled output of the OCR digitization pipeline.
M-005 | UC-003 | Sourcing Automation | CD-005 | Purchase Request Data | ⚑ Flag for Siyang to review — Purchase request data powers the sourcing recommendation logic and approval queue.
M-006 | UC-004 | Invoice Compliance | CD-006 | Contract Data | ⚑ Flag for Siyang to review — Contract data is ingested and linked to POs/invoices to drive compliance rules.
M-007 | UC-004 | Invoice Compliance | CD-001 | Purchase Order (PO) Data | ⚑ Flag for Siyang to review — PO data is linked to invoices/contracts for compliance and discrepancy matching.
M-008 | UC-004 | Invoice Compliance | CD-003 | Invoice Data (AP) | ⚑ Flag for Siyang to review — Invoice (AP) data is checked against POs/contracts to generate discrepancy flags.
M-009 | UC-005 | Partial Palantir Parity | CD-001 | Purchase Order (PO) Data | ⚑ Flag for Siyang to review — Partial Palantir Parity validates PO data end-to-end against Palantir outputs.
M-010 | UC-005 | Partial Palantir Parity | CD-002 | EAA Data (Marketing / Store Allocation) | ⚑ Flag for Siyang to review — Partial Palantir Parity validates EAA data end-to-end against Palantir outputs.
M-011 | UC-005 | Partial Palantir Parity | CD-003 | Invoice Data (AP) | ⚑ Flag for Siyang to review — Partial Palantir Parity validates Invoice (AP) data end-to-end against Palantir outputs.
M-012 | UC-005 | Partial Palantir Parity | CD-004 | Invoice Attachments | ⚑ Flag for Siyang to review — Partial Palantir Parity validates Invoice Attachments/OCR output end-to-end against Palantir outputs.
M-013 | UC-005 | Partial Palantir Parity | CD-005 | Purchase Request Data | ⚑ Flag for Siyang to review — Partial Palantir Parity validates Purchase Request data end-to-end against Palantir outputs.
M-014 | UC-005 | Partial Palantir Parity | CD-006 | Contract Data | ⚑ Flag for Siyang to review — Partial Palantir Parity validates Contract data end-to-end against Palantir outputs.
M-015 | UC-001 | Spend Visibility | CD-003 | Invoice Data - AP
M-016 | UC-001 | Spend Visibility | CD-007 | Supplier and Vendor Data
M-017 | UC-001 | Spend Visibility | CD-008 | Commodity and Category Data
M-018 | UC-001 | Spend Visibility | CD-009 | Purchase Order Line Data
M-019 | UC-001 | Spend Visibility | CD-010 | Purchase Accounting Allocation
M-020 | UC-001 | Spend Visibility | CD-011 | Activity Data
M-021 | UC-001 | Spend Visibility | CD-012 | Division Data
M-022 | UC-001 | Spend Visibility | CD-013 | Market Data
M-023 | UC-001 | Spend Visibility | CD-014 | Store Data
M-024 | UC-001 | Spend Visibility | CD-015 | Market-Store Relationship
M-025 | UC-001 | Spend Visibility | CD-016 | Vendor Type Data
M-026
M-027
M-028
M-029
M-030

## Use Case Tracker
Use Case ID | Use Case Name | Description | Status | Notes
UC-001 | Spend Visibility | - Coupa and EAA data curated and queryable in Silver/Gold via Unity Catalog | In Progress | Design prototype exists for Spend Visibility; testing-group feedback is planned. Taxonomy and data-source mapping discussions are also ongoing.
- Semantic layer returns accurate spend totals by vendor and category; validated against source data
- End users confirmed (category managers vs. business leadership)
- Agents can successfully query semantic layer and return spend insights
UC-002 | Document Digitization | - Invoice attachments accessible in Unity Catalog and feeding OCR pipeline | In Progress
- OCR output structured, mapped into ontology, and queryable by AI agents
- Line item detail unlocked and validated against sample of physical invoices
- Invoice digitization approach decided (OCR vs. governance process)
- Finance and Accounting buy-in secured; Marcy aligned on Coupa process changes
UC-003 | Sourcing Automation | - Sourcing recommendation logic tested and generating accurate, actionable savings opportunities |  | Taxonomy/sourcing discussions are active, but that does not prove the entire use case is in progress.
- Conversational interface live and accessible to category managers
- Category manager workflows defined and agreed upon
- Approval queue built, tested, and process agreed upon with procurement team
UC-004 | Invoice Compliance | - Contract data ingested and linked to POs and invoices in Unity Catalog |  | Invoice data work exists
- Compliance rules producing accurate discrepancy flags; tested against known invoice mismatches
- Discrepancy review queue live and routing correctly to category managers
- Compliance thresholds and escalation logic agreed with procurement team
UC-005 | Partial Palantir Parity | - Spend Visibility, Document Digitization, Sourcing Automation, and Invoice Compliance tested end-to-end and validated against Palantir outputs
- Palantir offramp executed; knowledge transfer for in-scope capabilities completed
- DevOps and support infrastructure in place for delivered capabilities

## Canonical Data Tracker
Canonical Data ID | Canonical Data Element | Definition | Data Domain | Source System | System Owner/POC | Extraction Method | Refresh Frequency | Status | Notes
CD-001 | Purchase Order (PO) Data | Indirect procurement purchase order data curated into Silver/Gold for spend visibility, sourcing automation, and invoice compliance matching. | Purchase Order | Coupa | kr_indirect_procurement_nonprod.coupa_api_nonprod_bronze.purchase_orders_v1 |  |  | Not Started | ⚑ Flag for Siyang to review — confirm definition and whether additional systems contribute PO data beyond Coupa.
CD-002 | EAA Data (Marketing / Store Allocation) | Marketing and store-allocation spend data curated into Silver/Gold for spend visibility; EAA migration is pending resolution of marketing/store allocation approach, with no Coupa equivalent today. | Spend Category | EAA |  |  |  | Not Started | ⚑ Flag for Siyang to review — confirm scope given EAA migration status and eventual Coupa equivalent.
CD-003 | Invoice Data (AP) | Accounts payable invoice header and line-item data used for OCR digitization, sourcing/compliance matching, and discrepancy detection. | Invoice | Coupa | kr_indirect_procurement_nonprod.coupa_api_nonprod_bronze.invoices_v1 |  |  | Not Started | ⚑ Flag for Siyang to review — confirm Coupa AP scope vs. Oracle AP (see row below).
CD-003 | Invoice Data (AP) |  | Invoice | Oracle AP |  |  |  | Not Started | ⚑ Flag for Siyang to review — confirm whether Oracle AP is an active parallel source or being retired/consolidated into Coupa.
CD-004 | Invoice Attachments | Scanned/PDF invoice attachments accessible in Unity Catalog, feeding the OCR digitization pipeline and enabling line-item detail extraction. | Invoice | Coupa | kr_indirect_procurement_nonprod.coupa_api_nonprod_bronze.invoice_attachments_v1 |  |  | Not Started | ⚑ Flag for Siyang to review — confirm attachment storage path and OCR pipeline vendor.
CD-005 | Purchase Request Data | Purchase requisition data used to power sourcing recommendation logic, the conversational sourcing interface, and category manager approval workflows. | Purchase Order | Coupa | kr_indirect_procurement_nonprod.coupa_api_nonprod_bronze.requisitions_v1 |  |  | Not Started | ⚑ Flag for Siyang to review — confirm requisition data scope and category manager workflow mapping.
CD-006 | Contract Data | Contract data ingested and linked to purchase orders and invoices to support compliance rules, discrepancy flags, and escalation logic. | Contract | Legal Tracker |  |  |  | Not Started | ⚑ Flag for Siyang to review — roadmap targets contract data ingestion in Q3/Q4 FY26, but Legal Tracker is scoped Post-MVP (Jan '27+) — confirm interim contract source or timeline alignment.
CD-006 | Contract Data | Contract header and term data used to connect suppliers, purchase orders, and invoices for contract-compliance checks, sourcing analysis, discrepancy detection, and escalation workflows. | Contract | Coupa | kr_indirect_procurement_nonprod.coupa_api_nonprod_bronze.contracts_v1
CD-007 | Supplier and Vendor Data | Supplier or vendor master data used for supplier-level spend aggregation, sourcing, compliance, payment-term analysis, vendor segmentation, and joining procurement documents to the correct supplier entity. | Vendor Master | Coupa | kr_indirect_procurement_nonprod.coupa_api_nonprod_bronze.suppliers_v1
kr_indirect_procurement_nonprod.coupa_api_nonprod_bronze.supplier_items_v1
CD-007 | Supplier and Vendor Data | EAA vendor-master data providing vendor classifications, organizational context, and reporting attributes. EAA vendor records display version or history behavior and require agreed current-state selection logic. | Vendor Master | EAA
CD-008 | Commodity and Category Data | Commodity taxonomy and category attributes used to classify requisitions, purchase orders, invoice lines, items, and suppliers for category-level spend visibility and sourcing analytics. | Spend Category | Coupa | kr_indirect_procurement_nonprod.coupa_api_nonprod_bronze.commodities_v1
CD-009 | Purchase Order Line Data | Purchase-order line-level data containing item, quantity, amount, commodity, accounting, and related document references. Supports line-level spend, invoice matching, compliance checks, and sourcing analysis. | Purchase Order | EAA
CD-010 | Purchase Accounting Allocation | Purchase-order accounting distribution data used to allocate procurement spend by account, project, division, market, cost center, or other financial and organizational dimensions. | Cost Center | EAA
CD-011 | Activity Data | Reference data describing purchasing or organizational activities associated with procurement transactions. Supports operational classification and spend segmentation. | Spend Category | EAA
CD-012 | Division Data | Division hierarchy and attributes used to roll up procurement spend and purchasing activity by Kroger organizational division. | Organization | EAA
CD-013 | Market Data | Market hierarchy and attributes used to analyze purchasing activity and spend below the division level and above the store level. | Organization | EAA
CD-014 | Store Data | Store reference data used to attribute purchasing activity and spend to specific stores or operating locations. | Organization | EAA
CD-015 | Market-Store Relationship | Bridge data connecting stores to markets and supporting validated organizational rollups from store to market and division. | Organization | EAA
CD-016 | Vendor Type Data | Vendor classification reference data used to segment suppliers by defined vendor-type categories and support sourcing and spend analysis. | Vendor Master | EAA
CD-017 | Vendor-Type Assignment | Data assigning vendors to one or more vendor-type categories. Supports supplier segmentation and category or sourcing analysis. | Vendor Master | EAA
CD-018 | Invoice Workflow and Exception History | Invoice-processing, workflow, status, or exception-history data used to understand invoice review outcomes and operational exceptions. Its role in core spend reporting versus operational monitoring requires confirmation. | Invoice | EAA
CD-019 | Invoice Payment Data | Payment records embedded within Coupa invoice payloads, including payable identifier, payment date, and payment amount. Supports paid-versus-unpaid analysis and invoice-payment traceability. | Payment | Coupa
CD-020 | Item Data | Item or catalog reference data used to associate procurement transactions with item numbers, manufacturer part numbers, commodity classifications, expenditure types, and asset categories. | Item | Coupa | kr_indirect_procurement_nonprod.coupa_api_nonprod_bronze.items_v1
CD-021 | User and Requester Data | User or requester information associated with procurement demand and approvals, including user identifier, employee number, division, location, cost center, and position where available. | User | Coupa | kr_indirect_procurement_nonprod.coupa_api_nonprod_bronze.users_v1
CD-022 | Purchase Order Change Data | Historical purchase-order change records used to analyze amendments, status changes, revised values, and the relationship between the current purchase order and prior versions. | Purchase Order | Coupa | kr_indirect_procurement_nonprod.coupa_api_nonprod_bronze.purchase_order_changes_v1

## Lists
Priority | Status | Data Domain | Source System | Extraction Method | Refresh Frequency | Canonical Data Element
High | Not Started | Vendor Master | Coupa | API | Real-time | Vendor Name
Medium | In Progress | Contract | EAA | Flat File | Daily | Vendor ID
Low | Blocked | Invoice | REMRENT | Manual | Weekly | Contract Value
| Complete | Purchase Order | RIVERMINE (Tango Pay) | Database Query | Monthly | Invoice Amount
| On Hold | Spend Category | Legal Tracker |  | Ad-hoc | PO Number
|  | Cost Center | TAX |  |  | Cost Center Code
|  | Payment | MAPS |  |  | Spend Category Code
|  | Item | SupplierConnect |  |  | Payment Terms
|  | User | M3 |  |  | …
|  | Organization | 100101
PTMS
340B
LICENSEHQ
FMSBT
VEBA
HOVS
RASCPROM
LCRGO
TLC
IPAYABLES
EMPAC
Invoice Gateway
Matchstix
EDI 810
Manual Invoice Entry
Oracle AP